## Sheet1
Action | Owner | Timeframe | Result | Progress made
Expand Current Green Schools Committee to focus on Energy | Denise Sheridan | 2012-09-01 | Added Elaine McKeogh MSc and all children | Complete
Complete Environmental review | Denise Sheridan | Oct&Nov 2012 | Areas to focus on light & heat management ; food production and revision of curriculum | Complete
Gather information on Heating consumption 2012-2014 | Denise Sheridan | Sept 2012-Mar 2014 |  | Complete
Introduce a sustainable car pooling service in line with parents. | Denise Sheridan | Sept 2012; Expanded in Sept 2013 | Year on Year benefits reduction in C02 and diesel requirements | Complete
Review Current preschool curriculum and develop an energy management curriculum in line with Aistear which can be integrated into the existing green focus on Litter and Waste management | Denise Sheridan | complete | Energy management not present in current curriculum further actions required | Complete
Insulate school and house more to reduce heat consumption - new double glazed windows put in in 2011 ; Side door in school insulated in 2014 and garage insulation will be put in in Mar 2012 ( directly underneath the preschool) | Nigel McKenna | 2011-2014 | Euros saved year on year | Complete
Replace all school light bulbs with Green Energy light bulbs | Nigel McKenna | 2013-09-01 | KhW saved year on year | Complete
Complete a Temperature Survey | Denise Sheridan | 2013-12-01 | Main area 20*C and toilet area 15*c | Complete
Ongoing Classroom heat management | Fiona Bourke & Rhona Sheridan | 2014-01-01 | Reduce main area to 18 *c and increase toilet area from 15*c to 18*c | Complete
Garden management - Introduce an annual review of garden plans /mapping in line with Elaine McKeogh Msc in Organic Horticulture to ensure that we are optimising the produce fruit ; veg ; plants etc in a sustainable manner | Denise Sheridan & Elaine McKeogh | 2013-09-01 | annual garden plan | Complete
Develop a list of projects which integrate energy management into our aistear focus; arts& crafts and recycling and litter management | Denise Sheridan & Elaine McKeogh | 2013-12-01 | Master lesson / project sheet | Complete
Pre & Afterschoolers project on Food production & Energy - Light; Water heat ; Dark - beans; peas ; potatoes | Rhona Sheridan & Elaine McKeogh & 13 preschool kids | Week 4 Jan 14 - Week 2 Mar | Recycled jars for planted beans; peas and recycled toilet rools used for potatoes - week by week review of impact of dark; heat; light on different food sources. Grown plants will be moved to school garden and taken home. Worm made from recycled toilet rolls. | Complete
Preschooler project on Natures ploughers and end to end microsystems- creating two indoor wormeries | Rhona Sheridan & Elaine McKeogh & 13 preschool kids | Week 1 Feb 14 | two indoor womeries created | Complete
Pre & afterschooler project on Seed production- end to end light ; sun; soil; shoots& roots; flowers; seed production ; seed harvesting | Rhona Sheridan & Elaine McKeogh & 13 preschool kids & 5 afterschool kids | Week 2 Feb 14 | Understanding of seed cycle and impoact of different energy types at different stages in the lifecycle. Planted harvested calendula seeds for mothers day presents | Complete
Preschoolers project on Wind & Water Energy Management | Rhona Sheridan & Elaine McKeogh & 13 preschool kids | Week 3 Feb14 | Created windmills and floating butterflies to understand the impact of wind. Created waves | Complete
Complete
Car pooling | Denise Sheridan - teaching 13 preschool kids about carpoolers and 5 active families involved. | Week 1 Sept 2012 - current |  | Complete
Pre & Afterschoolers project on Butterfly & Bird feeders and living organisms effect on energy management | Rhona Sheridan & Elaine McKeogh & 13 preschool kids | Week 1 Mar 14 |  | Complete
Lesson on heat management creating ladybird houses - focus heat management | Rhona Sheridan & Elaine McKeogh & 13 preschool kids | Week 2 Mar 14 |  | Complete
Herb garden management - energy management | Rhona Sheridan & Elaine McKeogh & 13 preschool kids | Week 1 Sept 2013 - current | Link with Litter and Waste management ; transition into home & partnership with parents | Complete
Learning about magnetism | Rhona Sheridan & Elaine McKeogh & 13 preschool kids | Wk 3 Mar 14 |  | Complete
Project on Cooking with energy learning about t sun ;light ; heat cold impacts on food and changing state of food | Rhona Sheridan & Elaine McKeogh & 13 preschool kids | Wk 1 Apr |  | Complete
Energy Home survey 1 | Denise Sheridan ; Rhona Sheridan ; Fiona Bourke | Week 3 Feb | 13 surveys shared - 9 returned. Main finding wasting water when brushing teeth. | Complete
Energy Star Awards | Denise Sheridan ; Rhona Sheridan ; Fiona Bourke | Week 4 Feb | Given out to the children as part of clare county council review on 25/2/14 | Complete
Energy Pledge | Preschool children and their families | Week 4 Feb | Pledge to turn off water when brushing teeth ; close doors; turn off lights - all families signed up | Complete
Clare County council on site visit 25/2/14 | Joan ; Denise Sheridan ; Rhona Sheridan ; Preschool kids | Wk 4 Feb | Recommendations - gather energy readings ; research SEAI resources to see what can be included in the curriculum; expand current code to include energy theme and develop a lesson plan on KhW preschool style | Complete
Afterschooler becomes Teacher on creating a rocket blaster | Darragh Hicky | Wk 4 Feb | Darragh- teacher for the day demonstrating how to make a rocket blaster
Afterschooler energy Quiz - 7 afterschoolers | Darragh; Ruby; Ava; Ruthie ; Clodagh ; Eoin; Max | Wed 26/11/13 | Average Score 7/11. | Complete | 70
Re do Afterschooler energy Quiz - 8 afterschoolers | Darragh; Ruby; Ava; Ruthie ; Patrick ; Sean ; Clodagh ; Eoin; Max | Thurs 27/2/14 | Average Score 10/11. 30% improvement once areas of renewables; alternatives; hydropower and dams were reviewed with all | Complete
Add a dedicated Web page for Green School Committee to Úlla Beag Website | Denise Sheridan | Thurs 27/2/14 |  | Complete
Sharing Energy Saving tips with parents | Denise with parents | Thurs 27/2/14 |  | Ongoing
Low Energy Day for preschoolers | Rhona & Fiona | Wed 5/3/14
Energy project day for Afterschoolers | Denise with kids | Wed 5/3 & 12/3
Send Energy saving tips out to all parents | Denise | Week 2 Mar |  | Complete
Integrate Energy theme to weekly Irish class for preschoolers | Fiona with kids | Week 1 Mar | Dún on Doras; Cas an solas; Múch an t-uisce
Collate all energy savings and convert into khW per child | Denise ; Nigel | Week 1 Mar

## Sheet2
Start date for period over which energy consumption was calculated
Finish date for period over which energy consumption was calculated
Number of school days in this period
Amount of Energy used in Kwh/Litres
Average number of Kwh used per person per day
How did you measure your Energy consumption
Year 1 (Review)
Electricity
2012-09-02
2012-09-09
5
635
7
Read the meter
Gas
2012-10-03
2012-10-04
2
1234
12
Conducted a manual audit
Oil
2012-10-03
2012-11-03
21
60
0.55
Bills
Other:
_______
n/a
n/a
n/a
n/a
n/a
n/a
Year 2 (Latest Figures)
Electricity
2013-09-02
2013-09-09
5
414
5
Read the meter
Gas
2013-10-03
2013-10-04
2
765
8
Conducted a manual audit
Oil
2013-10-03
2013-11-03
21
30
0.25
Bills
Other:
_______
n/a
n/a
n/a
n/a
n/a
n/a